### Star Trek Legacy 2

### Request for Proposal

ZeniMax Media Inc.

March 20, 2007

# Confidential

Subject to Change

Territories  		Worldwide

Release Date  		Nov 2008. Proposed schedule following.

Platforms  		PS3 (lead), Xbox 360, PC

Goal  	Sequel to Star Trek: Legacy for the ultimate Star Trek combat experience on next generation consoles and PC.

Budget	TBD  - See feature set for discussion points / budget itemization during proposal process. Budget is not to exceed X.

Basic Product Specification

A space combat game simulating a galactic war set in the Star Trek: The Next Generation Universe. The game will feature two levels of game play: Strategic and Tactical.

Strategic game play takes place on a large map of the Star Trek Universe. Here players move from star system to star system.  Decisions such as which systems to attack or defend and how are made here.

Tactical game play takes place on small local battle maps representing star systems in detail. Here players will command their starship in real time combat and execute on the attack or defense missions selected in the strategic mode.

The best game play example is the classic game Archon, a chess game where players then must actually fight out each battle. Turn based combat examples would include Heroes of Might and Magic or X-Com.

- Set in the TNG era of Star Trek

- Features all of the ships from TNG, some from TOS/TMP

- Contains real time ship combat as seen in the original Legacy

- Direct command of just one starship

- Minimum 16 player multiplayer

- Persistent player data (rank, ships, captains, etc.)

- Robust stat tracking

- Combat focused

- Extensive damage modeling

- (PC) Windows Vista ready

- (PC) Games for Windows compliant

Feature Set

Supremacy Mode

- Primary game mode

- Strategic and Tactical game play

- Large scale warfare on a persistent galactic map

- Persistent player data (ranking, ships and captains)

- Extensive stat tracking

- Can be played offline against the AI or online

Skirmish Mode

- Secondary game mode

- Full sandbox mode for the ultimate build-your-own-starfleet experience.

- Create any combination of skirmish size/ships/races with alternate skirmish scenarios (escort, planet capture etc.)

- Can be played offline against the AI or online

Game Play Features

- Real time space combat with massive starships

- Direct control of one ship

- Extensive damage modeling of all objects

- Epic scale, all objects appropriately sized

- Detailed subsystem targeting, able to pick ships apart

- Relevant use of all ship systems on all universe objects

  - Scanning

  - Tractor

  - Hail

  - Transport

- Interior bridge view

- Manual targeting

Multiplayer Features

- Server Based

- 16 players minimum

- Robust team/clan system

- Robust chat system

Developer Requirements

- Developer must be fully authorized and licensed by respective platform holders to develop on PS3 and Xbox 360.

- Developer must have experience with multiplayer code.

- Game must be built to applicable competitive technical and mechanical standards, per platform.

- All milestones, features and implementation/execution are subject to approval by Bethesda and Paramount/CBS.

License Requirements

- Builds for regular review with Licensor – all character/likeness and story design changes will need prior approval.

- Content must receive from the ESRB no greater than a T rating and equivalent ratings elsewhere within the territory.

- Cannot engage subcontractors without prior written approval by licensor.

Key Milestones

- April 6, 2007			Proposal Due Date

- April 20, 2007			Desired LOI/Contract Execution Date

- May 4, 2007	SCEA/SCEE/Microsoft/CBS Approval package

            - Game Design Document

            - Technical Design Document

            - Complete SCEA/SCEE Stage One documentation – per requirements.

            - Completed Xbox 360 concept submission form

- June 1, 2007	Deadline for SCEA/SCEE/MSFT/CBS concept approval (product codes or stage approvals)

- August 3, 2007			Technical Demo

            - One ship placed in one tactical map running in real time and able to rotate camera view.

- October 5, 2007			First Playable

            - A complete vertical slice that demonstrates key game play mechanics and technology for both the Strategic and Tactical modes. Art and audio may be temporary.

- May 2, 2008		Pre Alpha

            - SCEA/SCEE Stage 2 Submission

            - A playable build of the game representing around 50% of the development. This should include three or more levels that demonstrate key game play mechanics for all modes. Art and audio may be temporary, but should a representative of final content.

- June 6, 2008			Alpha

            - A playable build of the game representing 100% of the content, game play mechanics and modes of play. Art and audio should be 80% complete or better and representative of planned final quality.

- Aug 1, 2008		Beta

            - SCEA/SCEE Pre-tech and Microsoft Pre-cert

            - A playable build of the game representing 100% of the content, game play mechanics and modes of play. The game should be playable from start to finish. Art and audio should be representative of final quality.

- Sept 1, 2008		Gold Master

            - Final Submission to SCEA/SCEE and Microsoft.

- Oct 15, 2008		Release to Manufacture (RTM)

            - Approval from SCEA / SCEE and Microsoft.

Proposal Requirements

If interested, please respond no later than April 6, 2007.

The following information should be included in the proposal:

- Executive Summary containing a brief description of your design approach

- Company and proposed team profiles

- A description of your development process

- Asset delivery methods

- Quality control

- Proposed cost and payment details – with respective staffing plan and milestone delivery dates.

  - Breakdown by personnel by position, and time on project (example provided)

  - Man month totals

  - Any outsourced work/contractors, software licenses or hardware needs to be purchased by publisher.

Contact Info

Please direct proposals or questions to:

Todd Vaughn

VP of Development

Bethesda Softworks

1370 Piccard Drive, Suite 120

Rockville MD 20850

301-354-4262

Email (preferred): tvaughn@bethsoft.com